## IPL
S.no | Activity/Task | Assigned To | Start Date | End Date | Status
1 | Model1 (Facial Recognition and Smoker Propensity) | Gargee
1.a | Understand the current Smoker Model built and its input/output by Gargee | Gargee/Nivindya |  |  | Completed
| Share the input details for Smoker Propensity - E.H.R Data | Sivaguru |  |  | Completed
| Attributes in Rx, MIB, MVR has to be shared | Sivaguru |  |  | Completed
| Share mocked data for MIB, Rx, MVR | Sivaguru |  |  | Completed
| Build a model with Rx, MIB, MVR | Gargee
| Share the output of the Smoker Propensity model - "Smoker/Non Smoker", "Band - Occasional, regular etc" | Gargee
| Facial points to identify a person is a smoker or non smoker | Gargee
| Facial recognition to be built | Gargee
| Smoker/non smoker photos has to be shared with Gargee | Sivaguru
| Share the output of the Facial points model - "Smoker/Non Smoker", "Band - Occasional, regular etc" | Gargee
| Create Use case for Smoker Propensity and Facial analytics | Nivindya
1.b | Understand the Geo Location false data identification thoughts and its input/output from Gargee
MIB, Rx, NAIP Application Health questions response fields required - Smoker Model
Demographics - Need to share what state, what kind of diseases prone, mortality, climatic conditions etc.. - Geo Location
2 | Identify STP rules & Age and Amount criteria - Accelerated UW | Nivindya
3 | Create usecase for STP Rules Age and Amount | Nivindya
4 | Review the Facial Analytics usecase with core team and share with Gargee
4 | Model2 (Accelerated Underwriting) | Gargee
4.a | Understand the current Smoker Model built and its input/output by Gargee | Gargee/Nivindya |  |  | Completed
4.b | Build a model with Rx, MIB, MVR, Application data | Gargee
4.c | Share the output parameters for the Accelerated underwriting model | Gargee
4.d | Create Use case for Accelerated underwriting model | Nivindya
5 | Voice Bot - Enablers
5.a | CHI Application current work flow walkthrough and questions list review | Nithyaraj |  |  | Completed
5.b | CHI Application questions to be freezed by Nivinthya | Nivindya
5.c | Create usecase for CHI Voice bot | Nivindya
5.d | Output expected out of the CHI Voice bot | Nithyaraj
5.e | Identify feasibility of Voice bot implementation and access necessary resources for development | Nithyaraj |  |  | Completed
5.f | Develop Voice bot | Nithyaraj
5.g | Create Use case for Voice bot | Nivindya
6 | Create a process flow block diagram interlinking Model1, Facial Analytics, CHI Voice Bot, Model 2 usage before policy issue | Nithyaraj
7 | Create technial architecture diagram interlinking all the systems | Nithyaraj
8 | UI development to demonstrate the end to end work flow | Nithyaraj/ Sivaguru
9 | Create a ppt presentation for Round 1 - Check with Karthik | Kavi